## Sheet1
Task Number | Tasks | Duration | Weeks Since Start
1 | Set up Virtual Machine | 0.5
2 | Implement Existing Solutions | 2 | 0.5
3 | Evaluate Performance of Existing Solutions | 1 | 2.5
4 | Select BDL Approaches | 2 | 3.5
5 | Choose Datasets for Experimentation | 0.5 | 5.5
6 | Perform Data Exploration | 0.5 | 6
7 | Create Data Processing Steps | 1 | 6.5
8 | Choose Text Summarisation Model | 1 | 7.5
9 | Implement BDL Approaches | 1.5 | 8.5
10 | Test BDL Approaches | 1 | 10
11 | Evaluate BDL Solutions | 1 | 11
12 | Summarise Project Learning Points | 1 | 12