## Sheet1
Task Number | Tasks | Duration | Weeks Since Start
1 | Set up Virtual Machine | 0.2
2 | Perform Full Literature Review | 2 | 0.2
3 | Implement Existing Solutions | 2 | 2.2
4 | Evaluate Performance of Existing Solutions | 1 | 4.2
5 | Choose Datasets for Experimentation | 0.3 | 5.2
6 | Perform Data Exploration | 0.5 | 5.5
7 | Create Data Processing Steps | 1 | 6
8 | Choose Text Summarisation Model | 1 | 7
9 | Implement BDL Approaches | 2 | 8
10 | Test BDL Approaches | 1 | 10
11 | Evaluate BDL Solutions | 1 | 11
12 | Summarise Project Learning Points | 1 | 12
13 | Write up Conclusions and Discussion | 1 | 13